## Team
Initials | First | Last | Email | GitHub Username
EC | Edwin | Cazares | edwin.cazares18@gmail.com | edwincazares
MA | Mikkail | Allen | youngkels04@gmail.com | Mikkail04
SM | Shane | Malinak | shane.malinak21@gmail.com | mefodiiy
EM | Elliott | McKelvey | elliot.mckelvey@pm.me | obligatorytrudge
Note | All four team members contributed to Sprint 1 and are included in this updated Sprint Report.
|  |  | GitHub Repository: | https://github.com/edwincazares/cs555-teamC-gedcom-project

## Backlog
Sprint | Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
1 | US01 | Dates before current date | SM | Done | 70 | 150 | 62 | 140 | 6/21/2026
1 | US02 | Birth before marriage | SM | Done | 55 | 120 | 48 | 105 | 6/21/2026
1 | US07 | Less than 150 years old | EM | Done | 45 | 90 | 34 | 80 | 6/21/2026
1 | US08 | Birth before marriage of parents | EM | Done | 70 | 150 | 66 | 130 | 6/21/2026
1 | US27 | Include individual ages | MA | Done | 60 | 120 | 64 | 130 | 6/21/2026
1 | US28 | Order siblings by age | MA | Done | 80 | 180 | 72 | 165 | 6/21/2026
1 | US29 | List deceased | EC | Done | 60 | 120 | 45 | 95 | 6/21/2026
1 | US30 | List living married | EC | Done | 80 | 180 | 58 | 125 | 6/21/2026
1 | US31 | List living single | EC | Done | 70 | 150 | 65 | 140 | 6/21/2026
1 | US32 | List multiple births | EC | Done | 55 | 120 | 50 | 110 | 6/21/2026
1 | US35 | List recent births | EC | Done | 45 | 90 | 35 | 75 | 6/21/2026
1 | US36 | List recent deaths | EC | Done | 45 | 90 | 35 | 70 | 6/21/2026
2 | US03 | Birth before death | EC | Planned | 50 | 110
2 | US04 | Marriage before divorce | EC | Planned | 50 | 110
2 | US05 | Marriage before death | MA | Planned | 60 | 130
2 | US06 | Divorce before death | MA | Planned | 55 | 120
2 | US09 | Birth before death of parents | SM | Planned | 70 | 150
2 | US10 | Marriage after age 14 | SM | Planned | 50 | 100
2 | US11 | No bigamy | EM | Planned | 75 | 160
2 | US12 | Parents not too old | EM | Planned | 70 | 150
3 | US13 | Sibling spacing | TBD | Backlog
3 | US14 | Multiple births <= 5 | TBD | Backlog
3 | US15 | Fewer than 15 siblings | TBD | Backlog
3 | US16 | Male last names | TBD | Backlog
3 | US17 | No marriages to descendants | TBD | Backlog
3 | US18 | Siblings should not marry | TBD | Backlog
3 | US19 | First cousins should not marry | TBD | Backlog
3 | US20 | Aunts and uncles | TBD | Backlog
4 | US21 | Correct gender for role | TBD | Backlog
4 | US22 | Unique IDs | TBD | Backlog
4 | US23 | Unique name and birth date | TBD | Backlog
4 | US24 | Unique families by spouses | TBD | Backlog

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
6/13/2026 | 32 | 0 | 0 | 0 | 0
6/16/2026 | 29 | 3 | 144 | 325 | 26.6
6/18/2026 | 25 | 7 | 365 | 760 | 28.8
6/21/2026 | 20 | 12 | 634 | 1365 | 27.9

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates before current date | SM | Done | 70 | 150 | 62 | 140 | 6/21/2026
T01.01 | Check birth, death, marriage, and divorce dates against current date | SM | Done |  |  |  |  | 6/21/2026
T01.02 | Report future date errors with ID and user story number | SM | Done |  |  |  |  | 6/21/2026
T01.03 | Add acceptance test cases for future dates | SM | Done |  |  |  |  | 6/21/2026
US02 | Birth before marriage | SM | Done | 55 | 120 | 48 | 105 | 6/21/2026
T02.01 | Compare individual birth dates against marriage dates | SM | Done |  |  |  |  | 6/21/2026
T02.02 | Report errors for marriage before birth | SM | Done |  |  |  |  | 6/21/2026
US07 | Less than 150 years old | EM | Done | 45 | 90 | 34 | 80 | 6/21/2026
T07.01 | Calculate age at death or current age for living individuals | EM | Done |  |  |  |  | 6/21/2026
T07.02 | Report people older than 150 years | EM | Done |  |  |  |  | 6/21/2026
US08 | Birth before marriage of parents | EM | Done | 70 | 150 | 66 | 130 | 6/21/2026
T08.01 | Compare child birth dates to parents marriage and divorce dates | EM | Done |  |  |  |  | 6/21/2026
T08.02 | Report children born before marriage or too long after divorce | EM | Done |  |  |  |  | 6/21/2026
US27 | Include individual ages | MA | Done | 60 | 120 | 64 | 130 | 6/21/2026
T27.01 | Parse and store birth/death dates | MA | Done |  |  |  |  | 6/21/2026
T27.02 | Create calculate_age helper | MA | Done |  |  |  |  | 6/21/2026
T27.03 | Add Age field to Individuals output | MA | Done |  |  |  |  | 6/21/2026
T27.04 | Test living and deceased age cases | MA | Done |  |  |  |  | 6/21/2026
US28 | Order siblings by age | MA | Done | 80 | 180 | 72 | 165 | 6/21/2026
T28.01 | Create child sort helper using birth dates | MA | Done |  |  |  |  | 6/21/2026
T28.02 | Update family children display order | MA | Done |  |  |  |  | 6/21/2026
T28.03 | Test oldest to youngest sibling order | MA | Done |  |  |  |  | 6/21/2026
T28.04 | Fix sibling age sorting output | MA | Done |  |  |  |  | 6/21/2026
US29 | List deceased | EC | Done | 60 | 120 | 45 | 95 | 6/21/2026
T29.01 | Find individuals with death dates | EC | Done |  |  |  |  | 6/21/2026
T29.02 | Print deceased individuals section | EC | Done |  |  |  |  | 6/21/2026
T29.03 | Add GEDCOM test cases | EC | Done |  |  |  |  | 6/21/2026
T29.04 | Verify output formatting | EC | Done |  |  |  |  | 6/21/2026
US30 | List living married | EC | Done | 80 | 180 | 58 | 125 | 6/21/2026
T30.01 | Find living people with spouse family records | EC | Done |  |  |  |  | 6/21/2026
T30.02 | Print living married individuals section | EC | Done |  |  |  |  | 6/21/2026
T30.03 | Test married/deceased edge cases | EC | Done |  |  |  |  | 6/21/2026
T30.04 | Verify spouse relationships | EC | Done |  |  |  |  | 6/21/2026
US31 | List living single | EC | Done | 70 | 150 | 65 | 140 | 6/21/2026
T31.01 | Identify living people over age 30 | EC | Done |  |  |  |  | 6/21/2026
T31.02 | Filter individuals with no spouse family records | EC | Done |  |  |  |  | 6/21/2026
T31.03 | Print living single individuals section | EC | Done |  |  |  |  | 6/21/2026
US32 | List multiple births | EC | Done | 55 | 120 | 50 | 110 | 6/21/2026
T32.01 | Group siblings by birth date | EC | Done |  |  |  |  | 6/21/2026
T32.02 | Identify multiple births within families | EC | Done |  |  |  |  | 6/21/2026
T32.03 | Print multiple birth section | EC | Done |  |  |  |  | 6/21/2026
US35 | List recent births | EC | Done | 45 | 90 | 35 | 75 | 6/21/2026
T35.01 | Find individuals born in last 30 days | EC | Done |  |  |  |  | 6/21/2026
T35.02 | Add recent birth acceptance test record | EC | Done |  |  |  |  | 6/21/2026
T35.03 | Print recent births section | EC | Done |  |  |  |  | 6/21/2026
US36 | List recent deaths | EC | Done | 45 | 90 | 35 | 70 | 6/21/2026
T36.01 | Find individuals who died in last 30 days | EC | Done |  |  |  |  | 6/21/2026
T36.02 | Add recent death acceptance test record | EC | Done |  |  |  |  | 6/21/2026
T36.03 | Print recent deaths section | EC | Done |  |  |  |  | 6/21/2026
Sprint Review Results
Keep doing:
Continue using GitHub commits tied to specific user stories so individual work is visible.
Continue running the acceptance test file before submission and saving a clean Test Results file.
Continue keeping output readable with headers for Individuals, Families, and each demonstrated story.
Avoid:
Avoid leaving report fields incomplete after implementation is finished.
Avoid lexicographic ID sorting; GEDCOM IDs should be shown in natural numeric order.
Avoid last-minute code merges without checking the final output formatting.

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US03 | Birth before death | EC | Planned | 50 | 110
T03.01 | Compare birth and death dates for each individual | EC | Planned
T03.02 | Report individuals whose death occurs before birth | EC | Planned
US04 | Marriage before divorce | EC | Planned | 50 | 110
T04.01 | Compare marriage and divorce dates for each family | EC | Planned
T04.02 | Report divorce before marriage errors | EC | Planned
US05 | Marriage before death | MA | Planned | 60 | 130
T05.01 | Compare marriage date to husband and wife death dates | MA | Planned
T05.02 | Report marriages after death | MA | Planned
US06 | Divorce before death | MA | Planned | 55 | 120
T06.01 | Compare divorce date to spouse death dates | MA | Planned
T06.02 | Report divorce after death | MA | Planned
US09 | Birth before death of parents | SM | Planned | 70 | 150
T09.01 | Compare each child birth date with parent death dates | SM | Planned
T09.02 | Report child born after parent death errors | SM | Planned
US10 | Marriage after age 14 | SM | Planned | 50 | 100
T10.01 | Calculate spouse ages at marriage | SM | Planned
T10.02 | Report marriages where spouse was younger than 14 | SM | Planned
US11 | No bigamy | EM | Planned | 75 | 160
T11.01 | Compare overlapping marriages for individuals with multiple spouse families | EM | Planned
T11.02 | Report potential bigamy anomalies | EM | Planned
US12 | Parents not too old | EM | Planned | 70 | 150
T12.01 | Compare parent and child birth dates | EM | Planned
T12.02 | Report parent age anomalies beyond story limits | EM | Planned

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to descendants | Parents should not marry any of their descendants
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)

## Planning Notes
Planning Item | Notes
Sprint 1 Review | Team reviewed completed Sprint 1 stories, acceptance test output, and P3 feedback on 6/21/2026.
Sprint 1 Result | All Sprint 1 stories listed on the Sprint1 sheet were completed and demonstrated in the Test Results file.
Sprint 2 Planning | Team selected eight stories for Sprint 2 so each member owns two stories.
GitHub Repository | https://github.com/edwincazares/cs555-teamC-gedcom-project
Acceptance Test File | P4 Source Code.ged
Test Results File | P4 Output.txt
Keep Doing | Frequent commits, clear story ownership, and clean test output.
Avoid | Incomplete report fields, late merges, and output formatting issues.