## Team
Initials | First | Last | Email | GitHub Username
EC | Edwin | Cazares | edwin.cazares18@gmail.com | edwincazares
MA | Mikkail | Allen | youngkels04@gmail.com | Mikkail04
SM | Shane | Malinak | shane.malinak21@gmail.com | mefodiiy
EM | Elliott | McKelvey | elliot.mckelvey@pm.me | obligatorytrudge
Note | Sprint 2 completed with contributions from Edwin, Mikkail, and Shane.
|  |  | GitHub Repository: | https://github.com/edwincazares/cs555-teamC-gedcom-project

## Backlog
Sprint | Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
1 | US01 | Dates before current date | SM | Done | 70 | 150 | 62 | 140 | 6/21/2026
1 | US02 | Birth before marriage | SM | Done | 55 | 120 | 48 | 105 | 6/21/2026
1 | US07 | Less than 150 years old | EM | Done | 45 | 90 | 34 | 80 | 6/21/2026
1 | US08 | Birth before marriage of parents | EM | Done | 70 | 150 | 66 | 130 | 6/21/2026
1 | US27 | Include individual ages | MA | Done | 60 | 120 | 64 | 130 | 6/21/2026
1 | US28 | Order siblings by age | MA | Done | 80 | 180 | 72 | 165 | 6/21/2026
1 | US29 | List deceased | EC | Done | 60 | 120 | 45 | 95 | 6/21/2026
1 | US30 | List living married | EC | Done | 80 | 180 | 58 | 125 | 6/21/2026
1 | US31 | List living single | EC | Done | 70 | 150 | 65 | 140 | 6/21/2026
1 | US32 | List multiple births | EC | Done | 55 | 120 | 50 | 110 | 6/21/2026
1 | US35 | List recent births | EC | Done | 45 | 90 | 35 | 75 | 6/21/2026
1 | US36 | List recent deaths | EC | Done | 45 | 90 | 35 | 70 | 6/21/2026
2 | US03 | Birth before death | SM | Done | 45 | 90 | 42 | 85 | 7/5/2026
2 | US04 | Marriage before divorce | SM | Done | 50 | 100 | 46 | 95 | 7/5/2026
2 | US05 | Marriage before death | SM | Done | 60 | 130 | 54 | 115 | 7/5/2026
2 | US06 | Divorce before death | SM | Done | 55 | 120 | 50 | 108 | 7/5/2026
2 | US09 | Birth before death of parents | SM | Done | 70 | 150 | 66 | 145 | 7/5/2026
2 | US37 | List recent survivors | MA | Done | 55 | 110 | 48 | 100 | 7/5/2026
2 | US38 | List upcoming birthdays | MA | Done | 50 | 100 | 43 | 90 | 7/5/2026
2 | US10 | Marriage after age 14 | EC | Done | 50 | 100 | 52 | 105 | 7/5/2026
2 | US11 | No bigamy | EC | Done | 75 | 160 | 81 | 170 | 7/5/2026
3 | US12 | Parents not too old | EC | Planned | 70 | 150
3 | US13 | Sibling spacing | EC | Planned | 60 | 130
3 | US14 | Multiple births <= 5 | MA | Planned | 55 | 120
3 | US15 | Fewer than 15 siblings | MA | Planned | 45 | 90
3 | US16 | Male last names | SM | Planned | 55 | 110
3 | US17 | No marriages to descendants | SM | Planned | 80 | 180
3 | US18 | Siblings should not marry | EM | Planned | 70 | 150
3 | US19 | First cousins should not marry | EM | Planned | 90 | 210
4 | US20 | Aunts and uncles | TBD | Backlog
4 | US21 | Correct gender for role | TBD | Backlog
4 | US22 | Unique IDs | TBD | Backlog
4 | US23 | Unique name and birth date | TBD | Backlog
4 | US24 | Unique families by spouses | TBD | Backlog

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
6/13/2026 | 32 | 0 | 0 | 0 | 0
6/21/2026 | 20 | 12 | 634 | 1365 | 27.9
6/28/2026 | 15 | 5 | 258 | 548 | 28.2
7/5/2026 | 11 | 9 | 482 | 1013 | 28.5

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates before current date | SM | Done | 70 | 150 | 62 | 140 | 6/21/2026
T01.01 | Check birth, death, marriage, and divorce dates against current date | SM | Done |  |  |  |  | 6/21/2026
T01.02 | Report future date errors with ID and user story number | SM | Done |  |  |  |  | 6/21/2026
T01.03 | Add acceptance test cases for future dates | SM | Done |  |  |  |  | 6/21/2026
US02 | Birth before marriage | SM | Done | 55 | 120 | 48 | 105 | 6/21/2026
T02.01 | Compare individual birth dates against marriage dates | SM | Done |  |  |  |  | 6/21/2026
T02.02 | Report errors for marriage before birth | SM | Done |  |  |  |  | 6/21/2026
US07 | Less than 150 years old | EM | Done | 45 | 90 | 34 | 80 | 6/21/2026
T07.01 | Calculate age at death or current age for living individuals | EM | Done |  |  |  |  | 6/21/2026
T07.02 | Report people older than 150 years | EM | Done |  |  |  |  | 6/21/2026
US08 | Birth before marriage of parents | EM | Done | 70 | 150 | 66 | 130 | 6/21/2026
T08.01 | Compare child birth dates to parents marriage and divorce dates | EM | Done |  |  |  |  | 6/21/2026
T08.02 | Report children born before marriage or too long after divorce | EM | Done |  |  |  |  | 6/21/2026
US27 | Include individual ages | MA | Done | 60 | 120 | 64 | 130 | 6/21/2026
T27.01 | Parse and store birth/death dates | MA | Done |  |  |  |  | 6/21/2026
T27.02 | Create calculate_age helper | MA | Done |  |  |  |  | 6/21/2026
T27.03 | Add Age field to Individuals output | MA | Done |  |  |  |  | 6/21/2026
T27.04 | Test living and deceased age cases | MA | Done |  |  |  |  | 6/21/2026
US28 | Order siblings by age | MA | Done | 80 | 180 | 72 | 165 | 6/21/2026
T28.01 | Create child sort helper using birth dates | MA | Done |  |  |  |  | 6/21/2026
T28.02 | Update family children display order | MA | Done |  |  |  |  | 6/21/2026
T28.03 | Test oldest to youngest sibling order | MA | Done |  |  |  |  | 6/21/2026
T28.04 | Fix sibling age sorting output | MA | Done |  |  |  |  | 6/21/2026
US29 | List deceased | EC | Done | 60 | 120 | 45 | 95 | 6/21/2026
T29.01 | Find individuals with death dates | EC | Done |  |  |  |  | 6/21/2026
T29.02 | Print deceased individuals section | EC | Done |  |  |  |  | 6/21/2026
T29.03 | Add GEDCOM test cases | EC | Done |  |  |  |  | 6/21/2026
T29.04 | Verify output formatting | EC | Done |  |  |  |  | 6/21/2026
US30 | List living married | EC | Done | 80 | 180 | 58 | 125 | 6/21/2026
T30.01 | Find living people with spouse family records | EC | Done |  |  |  |  | 6/21/2026
T30.02 | Print living married individuals section | EC | Done |  |  |  |  | 6/21/2026
T30.03 | Test married/deceased edge cases | EC | Done |  |  |  |  | 6/21/2026
T30.04 | Verify spouse relationships | EC | Done |  |  |  |  | 6/21/2026
US31 | List living single | EC | Done | 70 | 150 | 65 | 140 | 6/21/2026
T31.01 | Identify living people over age 30 | EC | Done |  |  |  |  | 6/21/2026
T31.02 | Filter individuals with no spouse family records | EC | Done |  |  |  |  | 6/21/2026
T31.03 | Print living single individuals section | EC | Done |  |  |  |  | 6/21/2026
US32 | List multiple births | EC | Done | 55 | 120 | 50 | 110 | 6/21/2026
T32.01 | Group siblings by birth date | EC | Done |  |  |  |  | 6/21/2026
T32.02 | Identify multiple births within families | EC | Done |  |  |  |  | 6/21/2026
T32.03 | Print multiple birth section | EC | Done |  |  |  |  | 6/21/2026
US35 | List recent births | EC | Done | 45 | 90 | 35 | 75 | 6/21/2026
T35.01 | Find individuals born in last 30 days | EC | Done |  |  |  |  | 6/21/2026
T35.02 | Add recent birth acceptance test record | EC | Done |  |  |  |  | 6/21/2026
T35.03 | Print recent births section | EC | Done |  |  |  |  | 6/21/2026
US36 | List recent deaths | EC | Done | 45 | 90 | 35 | 70 | 6/21/2026
T36.01 | Find individuals who died in last 30 days | EC | Done |  |  |  |  | 6/21/2026
T36.02 | Add recent death acceptance test record | EC | Done |  |  |  |  | 6/21/2026
T36.03 | Print recent deaths section | EC | Done |  |  |  |  | 6/21/2026
Sprint Review Results
Keep doing:
Continue using GitHub commits tied to specific user stories so individual work is visible.
Continue running the acceptance test file before submission and saving a clean Test Results file.
Continue keeping output readable with headers for Individuals, Families, and each demonstrated story.
Avoid:
Avoid leaving report fields incomplete after implementation is finished.
Avoid lexicographic ID sorting; GEDCOM IDs should be shown in natural numeric order.
Avoid last-minute code merges without checking the final output formatting.

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US03 | Birth before death | SM | Done | 45 | 90 | 42 | 85 | 7/5/2026
T03.01 | Compare birth and death dates for each individual | SM | Done |  |  |  |  | 7/5/2026
T03.02 | Report individuals whose death occurs before birth | SM | Done |  |  |  |  | 7/5/2026
T03.03 | Add automated test for death before birth | SM | Done |  |  |  |  | 7/5/2026
US04 | Marriage before divorce | SM | Done | 50 | 100 | 46 | 95 | 7/5/2026
T04.01 | Compare marriage and divorce dates for each family | SM | Done |  |  |  |  | 7/5/2026
T04.02 | Report divorce before marriage errors | SM | Done |  |  |  |  | 7/5/2026
T04.03 | Add automated test for divorce before marriage | SM | Done |  |  |  |  | 7/5/2026
US05 | Marriage before death | SM | Done | 60 | 130 | 54 | 115 | 7/5/2026
T05.01 | Compare marriage date to husband and wife death dates | SM | Done |  |  |  |  | 7/5/2026
T05.02 | Report marriages after death | SM | Done |  |  |  |  | 7/5/2026
T05.03 | Add automated test for marriage after death | SM | Done |  |  |  |  | 7/5/2026
US06 | Divorce before death | SM | Done | 55 | 120 | 50 | 108 | 7/5/2026
T06.01 | Compare divorce date to spouse death dates | SM | Done |  |  |  |  | 7/5/2026
T06.02 | Report divorce after death | SM | Done |  |  |  |  | 7/5/2026
T06.03 | Add automated test for divorce after death | SM | Done |  |  |  |  | 7/5/2026
US09 | Birth before death of parents | SM | Done | 70 | 150 | 66 | 145 | 7/5/2026
T09.01 | Compare child birth date with parent death dates | SM | Done |  |  |  |  | 7/5/2026
T09.02 | Report child born after parent death errors | SM | Done |  |  |  |  | 7/5/2026
T09.03 | Add automated test for child born after parent death | SM | Done |  |  |  |  | 7/5/2026
US10 | Marriage after age 14 | EC | Done | 50 | 100 | 52 | 105 | 7/5/2026
T10.01 | Calculate spouse ages at marriage | EC | Done |  |  |  |  | 7/5/2026
T10.02 | Report spouses married before age 14 | EC | Done |  |  |  |  | 7/5/2026
T10.03 | Add automated test for underage marriage | EC | Done |  |  |  |  | 7/5/2026
US11 | No bigamy | EC | Done | 75 | 160 | 81 | 170 | 7/5/2026
T11.01 | Compare overlapping spouse family records | EC | Done |  |  |  |  | 7/5/2026
T11.02 | Report active overlapping marriages | EC | Done |  |  |  |  | 7/5/2026
T11.03 | Add automated test for overlapping marriages | EC | Done |  |  |  |  | 7/5/2026
US37 | List recent survivors | MA | Done | 55 | 110 | 48 | 100 | 7/5/2026
T37.01 | Find recently deceased individuals | MA | Done |  |  |  |  | 7/5/2026
T37.02 | List living spouses and children as survivors | MA | Done |  |  |  |  | 7/5/2026
T37.03 | Add automated test for recent survivors | MA | Done |  |  |  |  | 7/5/2026
US38 | List upcoming birthdays | MA | Done | 50 | 100 | 43 | 90 | 7/5/2026
T38.01 | Find living individuals with birthdays in next 30 days | MA | Done |  |  |  |  | 7/5/2026
T38.02 | Print upcoming birthday section | MA | Done |  |  |  |  | 7/5/2026
T38.03 | Add automated test for upcoming birthdays | MA | Done |  |  |  |  | 7/5/2026
Sprint Review Results
Keep doing:
Continue requiring each completed user story to include at least one automated test.
Continue adding analysis notes to customer output so failure modes are clear.
Continue using natural numeric ID sorting and fixed-width tables for readable output.
Avoid:
Avoid leaving test ownership unclear when multiple team members contribute code.
Avoid relying only on manual acceptance output when a story needs an automated test.
Avoid late or missing contributions, because it creates uneven sprint workload.

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US12 | Parents not too old | EC | Planned | 70 | 150
T12.01 | Compare parent and child birth dates | EC | Planned
T12.02 | Report parent age anomalies beyond story limits | EC | Planned
T12.03 | Add automated test for parent age limits | EC | Planned
US13 | Sibling spacing | EC | Planned | 60 | 130
T13.01 | Compare birth dates of sibling pairs | EC | Planned
T13.02 | Report sibling spacing anomalies | EC | Planned
T13.03 | Add automated test for sibling spacing | EC | Planned
US14 | Multiple births <= 5 | MA | Planned | 55 | 120
T14.01 | Group siblings by birth date | MA | Planned
T14.02 | Report groups with more than five siblings born together | MA | Planned
T14.03 | Add automated test for large multiple birth groups | MA | Planned
US15 | Fewer than 15 siblings | MA | Planned | 45 | 90
T15.01 | Count children in each family | MA | Planned
T15.02 | Report families with 15 or more siblings | MA | Planned
T15.03 | Add automated test for sibling count limit | MA | Planned
US16 | Male last names | SM | Planned | 55 | 110
T16.01 | Compare male child surnames with family surname | SM | Planned
T16.02 | Report male surname mismatches | SM | Planned
T16.03 | Add automated test for male last names | SM | Planned
US17 | No marriages to descendants | SM | Planned | 80 | 180
T17.01 | Build ancestor and descendant relationships | SM | Planned
T17.02 | Report marriages between descendants and ancestors | SM | Planned
T17.03 | Add automated test for descendant marriage | SM | Planned
US18 | Siblings should not marry | EM | Planned | 70 | 150
T18.01 | Identify sibling relationships from family records | EM | Planned
T18.02 | Report sibling marriages | EM | Planned
T18.03 | Add automated test for sibling marriage | EM | Planned
US19 | First cousins should not marry | EM | Planned | 90 | 210
T19.01 | Identify first cousin relationships | EM | Planned
T19.02 | Report first cousin marriages | EM | Planned
T19.03 | Add automated test for first cousin marriage | EM | Planned

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to descendants | Parents should not marry any of their descendants
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)

## Planning Notes
Planning Item | Notes
Sprint 2 Review | Team reviewed completed Sprint 2 code, automated tests, and acceptance test output.
Sprint 2 Result | Nine Sprint 2 stories were completed and demonstrated.
Automated Testing | Sprint 2 introduced automated unittest coverage for every completed Sprint 2 story.
Analysis Improvement | Customer output now includes additional explanation for US10 and US11 to explain why the failure modes matter.
Sprint 3 Planning | Team selected eight stories for Sprint 3 with ownership and estimates.
GitHub Repository | https://github.com/edwincazares/cs555-teamC-gedcom-project
Acceptance Test File | teamC_sprint2_acceptance_test.ged
Test Results File | teamC_sprint2_test_results.txt
Automated Test File | test_user_stories_p6.py